## Start Here
L&D Project Tracker
Tracks every training request from intake to evaluation: who owns it, where it is in ADDIE, how big it is, and whether it's on time.
The Art of Learning Design™ · Portfolio sample
What's in this workbook
Tracker | One row per training request. Dropdowns keep entries consistent; % complete, build time, and status flags calculate.
Dashboard | Counts by status and phase, overdue items, and average progress. Updates as the tracker changes.
Lists | The options behind the dropdowns, plus the engagement levels that set build time.
How to use it
Light yellow cells | Inputs. Pick from the dropdown or type a value.
White cells | Formulas. Don't type over them.
Example rows | The tracker is filled with example projects so the dashboard has something to show. Replace them with your own.

## Dashboard
Dashboard
Everything here is calculated from the Tracker tab.
The Art of Learning Design™ · Portfolio sample
Active projects | 6
Overdue | 1
Due in the next 7 days | 1
Average % complete (active) | 29.17%
Status | Projects | ADDIE phase | Projects
Pending assignment | 1 | Analyze | 2
Not started | 1 | Design | 2
In progress | 3 | Develop | 1
On hold | 1 | Implement | 1
Completed | 2 | Evaluate | 0
Cancelled | 0 | Evergreen | 0
Phase counts include active projects only.

## Tracker
Training Project Tracker
Update status and phase each time they change. Flags compare the due date to today.
The Art of Learning Design™ · Portfolio sample
Project | Business unit | Owner | Request type | Modality | Level | Status | ADDIE phase | % complete | Requested | Start | Due | Build weeks | Planned finish | Flag | Notes
VA IRRRL quick reference | Retail lending | Anita | New product training | QRG / Job aid | Level 2 | Completed | Evaluate | 100% | 2026-08-03 | 2026-08-10 | 2026-08-31 | 3 | 2026-08-31 | Done | Piloted with six loan officers; two wording fixes made.
Close-fast tips job aid | Retail lending | Anita | Update existing training | QRG / Job aid | Level 2 | Completed | Evaluate | 100% | 2026-08-17 | 2026-08-24 | 2026-09-14 | 3 | 2026-09-14 | Done | Built from SME interviews on top delay reasons.
Customer service new hire refresh | Servicing | Anita | Departmental training | vILT | Level 3 | In progress | Develop | 50% | 2026-09-01 | 2026-09-14 | 2026-10-30 | 5 | 2026-10-19 | On track | Day 1 deck and scorecard drafted; Week 2 role plays in build.
Call quality scorecard update | Servicing | Team lead | Update existing training | QRG / Job aid | Level 1 | In progress | Implement | 75% | 2026-09-21 | 2026-09-28 | 2026-10-16 | 2 | 2026-10-12 | Due soon | Calibration session with QA scheduled.
Loan officer onboarding: week 1 | Retail lending | Anita | Departmental training | ILT | Level 3 | Not started | Analyze | 0% | 2026-10-05 | 2026-11-02 | 2026-12-11 | 5 | 2026-12-07 | On track | Scoping meeting set with sales leadership.
LOS upgrade: new disclosure screens | Operations | Trainer 2 | System training | Video | Level 2 | On hold | Design | 25% | 2026-09-08 | 2026-09-21 | 2026-10-09 | 3 | 2026-10-12 | Overdue | Waiting on vendor release date.
Escrow shortage explainer | Servicing | Trainer 2 | New product training | eLearning | Level 2 | In progress | Design | 25% | 2026-09-28 | 2026-10-05 | 2026-10-23 | 3 | 2026-10-26 | On track | Storyboard in SME review.
Fee waiver policy attestation | Compliance | Anita | New attestation | FAQ | Level 1 | Pending assignment | Analyze | 0% | 2026-10-09 |  |  | 2 |  | Needs dates
Formulas:
Planned finish = IF(OR([Start]="",[Build weeks]=""),"",[Start]+[Build weeks]*7)
Flag = IF([Project]="","",IF(OR([Status]="Completed",[Status]="Cancelled"),"Done",IF([Due]="","Needs dates",IF([Due]<TODAY(),"Overdue",IF([Due]-TODAY()<=7,"Due soon","On track")))))
Note on N5: Start date plus build weeks for the engagement level (see Lists). Compare to the agreed due date.

## Lists
Lists & Reference
Edit these lists to change the dropdown options.
The Art of Learning Design™ · Portfolio sample
Status | ADDIE phase | % complete | Request type | Modality
Pending assignment | Analyze | 0% | New product training | ILT
Not started | Design | 25% | System training | vILT
In progress | Develop | 50% | Departmental training | eLearning
On hold | Implement | 75% | Update existing training | Video
Completed | Evaluate | 100% | New attestation | QRG / Job aid
Cancelled | Evergreen | 100% | Update existing attestation | FAQ
Engagement level |  | Build weeks |  | What it looks like
Level 1 |  | 2 |  | Passive: learner mostly consumes information. Short webinar with Q&A or media with an FAQ.
Level 2 |  | 3 |  | Some interactivity. Up to three objectives; may include an assessment or attestation; standard participant guide.
Level 3 |  | 5 |  | Highly interactive. Four or more objectives; video, exercises, participant and facilitator guides, slides, assessments.
Note on D17: Level 3 builds take four to six weeks; five is used as the planning midpoint.